## Sheet1
Milestones | Time Limit | Section/Module | Functionality | Description/Reference | Solution
1 | 7 Days | Testing & Admin Panal | Select course(which they would like to connect) - When click on course, subject will be fetched from course Api - Admin can enter question of each subject for test creation & duration of total exam | Checking of all API's and there responses and adjustment of the app enviorment. | Testing all the API's on Postman and Start to working on test creation module which mainly includes Question Level (Easy, Medium & Difficult)
2 | 7 Days | Admin Panal | For question choose - there will be 2 models - 1) Automatic test generator (Admin can select subject>chapter>topic & enter how any question they want to add in this topic & question level also(Difficult/Medium/Hard)) – alternate question will be picked from these topic - 2) Manual question picker from subject>chapter>topic - When clicked on online test - test will conduct online. All question will be showed & admin can pick manually.
3 | 7 Days | Student Panal | Working on the progress Bar according to ther result progress.When click on subject, comparion will be showed with topper. Chapter wise comparison performed | Practise Paper