## Sheet1
Tasks | No of Hours | Client's Comments | Solutions | Budget
Sprint 1 (1-2 week to Complete)
Top Bar Task1 |  | integrate the newly designed top section | My Ux/Ui designer will make the new design and convert it into Bootstrap and then integrate or you can provide us the html files and we can integrate it to the main application | 70 Usd
|  | From the drop down menu on user’s picture: | You old navigation missing these options 1 Profile 2 Edit Profile (that is our task to add these two options) Then we will link this menu to their respective pages
Link the profile to the profile page. Link settings to settings page and link log out to log out page.
Edit profile should be be linked to profile and allow editing functionality
Side Bar Task 2 |  | integrate the newly designed side section utilizing the above link Link all of the menu buttons to the correct pages | We can create the new side ar design or if you already have that we can easily Implement into the main application and yes obiviously the buttons in side bar will redirect to respective pages | 70 Usd
Dispute Modal(PopUp) Task 3 |  | When click on dispute button which yu can find (in contract section of side bar) A pop up modal will open and where you need to add following input fields so you can get more data. Header: Help us to improve Densub Reasons: Feedback about your new Densub experience Feedback about a broken feature New ideas to make Densub a better product Detail box: Please include as much information as possible | before we implement this I have two questions. 1 Do we have an api which can get this data from client side and save it to database (if not we will create it) 2 Once the dispute is submitted where you want to show it After collecting the correct requirements we are gonna complete this Task 3 | 120 Usd
Profile Top Section Task 4a |  | Reflect Position Type and Ratings Reflect correct profile statuses Profile statuses: Inprogress, Pending, Verified, Rejected Select an icon for each stat | What we do is to use Get API of User Profile and get the specific result and show at the user Profile Top Section | 100usd
Dental license expiration date UI Task 4b |  | Dental license expiration date UI Currently we show this in a banner on top of the page. I want to show it this way ( “PA - DH071152 exp date Jan,1,2021”) or PA - DH071152 30 Days to expire or PA-DH071152 is expired ) show this message as a pop up “Update your professional dental license to apply for jobs” if user has more than one license show the second under the first one ( or propose a better UI for showing more than one licenses | Get the Api and Using Angular pipe to show what ever data format you want
profile viewers Task 5 |  | profile viewers Show profile picture of the practices that has viewed staff’s public profile by default show the data for the past 30 days implement filter system filter options: ( This week, Last week, This month, Last month) Recommended Jobs section check the accuracy of implementation of this logic and if it is not implemented properly it should be fixed) Implement distance filter Show a list of jobs that are posted within the certain miles that the user is willing to travel. The staff user enters this data while creating profile The same position type as user’s position type Note: "Final offer received" tag should be blinking. It blinks on Applications page also) | Well that task need mroe details I canno suggest you any solution right now we will discuss it in more detaisl to get this thing done | Cannot Suggest Any Budget
Message and Calender Section Task 6 |  | Message Section Details show this on the right side of the calendar show a list of the latest received messages for each messages show: practice picture, practice name, and little bit of the message, received on date and time stamp each message should be clickable to the messages page for that specific job Clrender Section Details Implement a modern looking calendar with nice UI and features Link “update calendar” button to the “staff profile page/mycalendar section” increase the size of the calendar ( calendar ‘s width should be as big as half of the page change the color coding. (sanaz will provide new color codes) Add “Modified Availability” to the color code section and change the word “Assignments” to “Booked” Reflect the same functionality we reflect on the calendar in profile creation section Show a list of booked assignment(s) - only temporary assignments- when user hovers over a certain date for each assignment show: practice’s name, and job time For “Modified availability” days: show the start and end time of the availability. | The Main Point here is to change the lay out and convert these two sections to have half/half width of the page and divide it into Two section then after that get the Data from an API anbd post the things accordingly | 150 USD
Sprint 2 (1-2 week to Complete)
Listing Section Task 1 |  | create pagination for the listings Provide me a list of the statuses for (Invitations, applications, jobs, timesheets, payments) status tag color should be updated (sanaz will provide the new color code) Invitations: filter options: “All, New, Viewed, Declined, Expired” question to developer: Does “Expired” status exist for Invitations? Do we show “Job is no longer available” tag for “Expired” invitations? do not show invitations with “Applied” status in this list Note: After user views a new invitation the status of the invitation should change to “Viewed” from “New” Applications: filter options: “All, Applied - waiting for approval, Declined, Final Offer Received” Declined invitations should not show in applications list Applications that are tagged as ”Final offer received - waiting for approval” should be shown on top of the list Reflect the ( Accept and Decline) functionality. for Accept show a checkmark icon and for Decline show an X icon. Assignments change the name from “Assignments “ to “Upcoming Assignments ” only show assignments with “Upcoming status” job status tag color : Yellow - sanaz will provide color code Inprogress Assignments Duplicate the upcoming assignments listings. Only show jobs with “Inprogress status” job status tag color: orange Awaiting Approval & Pay change the name of “Timesheets” to “Awaiting Approval &Pay” filter options ( reflect all of the statuses related to timesheet) : All, Submitted - Pending Approval, Approved, Revision Requested, Revision Rejected clickable to assignment individual page timesheet tab Listing view: looks the same as upcoming, reflect estimated wages. status tag color: salmon pink Completed change the name from “Payments” to “Completed” Filter options ( reflect all of the statuses for jobs with completed status) : All, Completed, Completed- timesheet not submitted, Completed-Not paid, Completed- Hired, Completed - Marked as paid by staff in the job listing on the Right side show: payment method ( “e-pay” for online payment and “Offline” for offline payments), total payment that was paid. Show payment with decimal point (ie: $123.00 or 123.45) Clickable to assignment individual page, payment tab show the system we created in the Ratings section here in payments ( If staff has not rated the practice for a specific job show the “Rate Now” link. If practice has rated staff, show the rating that practice has provided with a date stamp. if staff has rated practice show the rating staff has provided with date stamp) Ratings remove the “Ratings” list it is not needed anymore - NOTE: check out the implemented Rate system and reflect it on the “Completed” listing before removing this listing | Solution 1 Filter should work accordingly we will implement paigintaion using Angular built it paignation library Sanaz can provide new color code for status change old List of Statuses according to these: 1 Inivitaions (Will implement according to Demand) 2 Applications (Will implement according to Demand) 3 Assignments (Will implement according to Demand) 4 Inprogress Assignments (Will implement according to Demand) 5 Awaiting Approval and Pay (Will implement according to Demand) (old name was timesheet) 6 Completed (Will implement according to Demand) 7 Ratings (Will implement according to Demand) | 250Usd
Short Section Task 2 |  | Insights insights only affects the shortcut buttons The Insights by default should be filtered on a “Monthly” basis and filterable for 1 week, 2 weeks, This month, Last Month, Last 3 months, Last 6 months, This Year, Last Year, All time , Date Range” see this link for reference Monthly Recurring Revenue - Baremetrics Demo the date range field should be part of the insights not a separate field Add time iteration (Daily, Weekly, Monthly, Annual) This iteration should be coordinated and make sense. for example if you pick a time period of 20 days the time iteration available should only be daily and weekly since there is not enough data to show monthly and annual time iteration. they should be grayed out. If you pick a time period that covers 90 days, then you can have a time iteration of daily, weekly and monthly with annual being grayed out. shortcut buttons Remove these 3 shortcuts ( Timesheets, Payments, Ratings) - I am only going to keep ( Invitations, Applications and All Assignments) shortcuts Move the remaining 3 shortcuts to under the Listings section implement the filters on the buttons and the graphs should work properly link “Invitations' ' shortcut button to “Invitations” page. “Applications'' shortcut button to “applications” page and “All Assignments” shortcut button to “My assignments pages , All assignments tab” Invitations default value shown on the counter: sum of all of the invitations received confirm if this status “expired” exist or not Applications default value shown on the counter: sum of all of the applications sent by user All Assignments Default for value shown on the counter: sum of all of the assignments in different statuses | Three Main tasks need to be done 1 The shorcut filter should work according to demand (if we need to re write the api we can) 2 extra Short Cut should be removed 3 Shortcut should show the data | 250USD
Sprint 3 (1-2 week to Complete)
Set Goal Section Task 1 |  | Increase the size by 1/3rd and move it to the bottom of the page Allow users to enter 2 sets of data. 1. Earnings goal 2. Hours to work goal. After user enters the data for one of the following time specifications: (Daily, Weekly, Monthly, or Annual basis). then, system calculates it for the rest of the time basis To calculate the goal met: Divide Total payments to the goal set by user Total payments: Add the total of the submitted timesheets + total amount of unsubmitted timesheets + plus total amount of marked as paid assignments functionality example: staff select weekly time iteration which it has set a weekly budget of $250 and staff selects insight time period of last 3 months (sept-nov). The total staff earned in Sept $500, Oct 1,000, Nov 1,000= $2500 and there is 13 weeks…. calclulation should be $2500/13 weeks = $192.30/week or $192.30/$250= 76.9% show a percentage of the goal met so far on the graph User can toggle timeline displays .timelines are (Weekly, Monthly, Yearly) goal is editable at any time Set Goal pop up UI - see attachment for reference - Add a drop down menu menu items are: (1. Earnings 2. Hours To Work) Title: Set Your Goals Subtitle: if Earnings is selected show this text: “ Set your earning’s goal and track your progress at any time If “hours to work” is selected: “ Set howmany hours you are planning to work and track your progress at any time” | The main task here is to recreate the Goal Section We can implement chart.js or amcharts library for this We will see the api if its sending the deisre data and result and then we will implment it | 250 USD
Statistic Section Task 2 |  | increase the size and move it to the bottom of the page. this section should be parallel to the Set Goals Note: API’s are written, only need to be reflected Note: check the accuracy of the APIs Earnings = should be the sum of the followings: total amount of marked as paid by staff total amount of system calculated- if timesheet is not submitted- total amount of paid via offline total amount of paid via stripe Days Worked= sum of temporary assignments accepted. if user cancels an assignment, this will affect the total Hours Worked = sum of hours of the jobs Average Rate /Hr Miles travelled= sum of miles traveled Ratings = should be the sum of total ratings sent and received | Major Task to do: 1 Check Apis and check thier data 2 Reflect the correct data to statistic 3 Rest the work will be implemented according to demand | 150 Usd
Analytics Page Task 3 |  | these are the same data we are showing in statistics section but in a graph mode APIs are already written, should be reflected on the page Implement the position type, date and filters by default show this for the past 30 days Earnings Show total amount of earnings in the jobs with the following statuses: (completed- marked as paid by staff, completed- timesheet not submitted, completed not paid, complete- paid via online, completed paid via offline) Average Rate /Hr Days Worked Hours Worked | Solution: 1 Test Apis 2 Test Graphs 3 test Filters 4 Implement this section according to demand | 250 USD
The End